## RiskRegister - Project 2
Date Identified | Risk No. | Deliverable | Risk Description | Category | Potential Impact Description | Risk Owner | Likelihood of Occurrence | Impact | Likelihood Risk Value | Impact Risk Value | Risk | Response | Response Comments | Status | Loss Hours/Cost | Preventative Risk Hours/Cost | Response | Preventive Strategic Plan | Contingency Strategic Plan | Date of Response Implemented
[7 empty] | Low, Medium, High | Low, Medium, High | Likelihood | Impact
04/15/2024 | 1 | Store Management System | Integration failure of different modules | Technical | Delays in operation, increased errors, potential revenue loss | Kevin Simon | Medium | High | 5 | 5 | 10 | Mitigate | Ensure all modules are compatible before full-scale deployment | New | 5w/$40,000 | $10000 | Mitigate | Prioritize modular flexibility and fallback options | Establish manual processing systems as backup | TBD
04/15/2024 | 2 | Access across multiple devices | Incompatibility with different operating systems or sizes | Compatibility | Restricted access from certain devices may limit operational flexibility | Kevin Simon | High | Medium | 5 | 4 | 9 | Mitigate | Develop using responsive and adaptable frameworks | New | 4w/$40,000 | $5000 | Mitigate | Design a system that adjusts to various screen sizes and OS | Create alternative access options for critical functions | TBD
04/16/2024 | 3 | User-friendly interface | Usability issues due to complex functionalities | Usability | Frustration among employees, reduced efficiency, possible decrease in system use | Kevin Simon | High | Medium | 3 | 4 | 7 | Mitigate | Test with real users to refine interface | New | 2w/$4000 | $3000 | Mitigate | Design with emphasis on simplicity and clarity | Provide training and support for system users | TBD
04/16/2024 | 4 | Comprehensive reporting capability | Insufficient reporting tools | Functional | Inability to make informed decisions due to poor data visualization and reporting | Kevin Simon | Medium | High | 3 | 4 | 7 | Mitigate | Integrate advanced reporting tools and analytics | New | 5w/$4000 | $0 | Mitigate | Integrate with business intelligence tools for better insights | Develop manual reporting protocols as interim measure | TBD
04/17/2024 | 5 | Disruption in daily operations | The operational risk involves the potential for disruptions in daily operations due to system failures, inadequate training, or unforeseen events. | Operational | This risk could lead to downtime, loss of productivity, customer dissatisfaction, and revenue loss. | Kevin (Project Manager) | Medium | High | 5 | 6 | 11 | Mitigate | Develop comprehensive operational procedures and contingency plans for handling system outages or emergencies. Provide thorough training for employees to ensure they can effectively use and troubleshoot the system. Conduct regular maintenance and system checks to identify and address potential issues proactively. | Active | 3w/$7000 | $5000 | Mitigate | Establish backup systems, and create escalation procedures for critical issues. | Have a dedicated support team, and maintain communication channels for rapid response during emergencies. | TBD
04/19/2024 | 6 | Meeting regulatory compliance | The regulatory compliance risk involves the possibility of failing to meet legal and regulatory requirements related to data privacy, tax reporting, and other industry-specific regulations. | External | Non-compliance could result in fines, legal actions, reputational damage, and operational disruptions. | Kevin (Project Manager) | Low | High | 2 | 10 | 12 | Mitigate | Conduct a thorough review of relevant regulations and ensure the system design and processes comply with all applicable laws. Implement data protection measures, tax reporting functionalities, and audit trails to demonstrate compliance. Regularly update policies and procedures to reflect changes in regulations and conduct internal audits to verify compliance. | Active | 3w/$20,000 | $11000 | Mitigate | Engage legal experts for compliance review, and integrate compliance checks into system workflows. | Have contingency plans for regulatory audits, and maintain open communication with regulatory authorities. | TBD
04/21/2024 | 7 | Store Management System | Reliance on external suppliers for critical services or products, posing risks of disruptions and lack of control. | Supplier | Reliance on a single vendor for critical system components, potential delays or disruptions | Kevin Simon | High | Medium | 5 | 3 | 8 | Mitigate | Identify alternative vendors and diversify supplier relationships | New | 4w/$30,000 | $8,000 | Avoid | Establish contracts with multiple vendors and maintain vendor relationships | Develop fallback procedures and emergency protocols in case of vendor failure | TBD
04/25/2024 | 8 | Store Management System Implementation | Data Security Breach | Security | The system may be vulnerable to cyber threats, leading to unauthorized access or data breaches, compromising sensitive customer and financial information. | IT Team | Medium | High | 5 | 6 | 11 | Mitigate | Regular security audits and employee training will help minimize the risk of data breaches. | Ongoing | 1w/$8,000 | $2,000 | Enhanced security measures and employee training | Implement multi-factor authentication and encryption protocols to safeguard sensitive data. | Develop a contingency plan for rapid response and damage control in the event of a security breach. | TBD
04/27/2024 | 9 | Store Management System Implementation | Budget Overrun | Financial | The project may exceed the allocated budget due to unforeseen expenses or scope changes. | Kevin Simon: Project Manager | High | High | 3 | 3 | 6 | Mitigate | Regular budget monitoring and change control procedures will help mitigate the risk of budget overrun. | Ongoing | 3w/$15,000 | $4,000 | Mitigate | Implement a contingency reserve for unexpected expenses and prioritize project tasks to stay within budget constraints. | Identify potential areas for cost-saving measures or reallocation of resources if necessary. | TBD
04/22/2024 | 10 | Store Management System Implementation | Inadequate User Training | Operational | Lack of proficiency in using the new system, leading to errors and reduced productivity | Kevin Simon | High | Medium | 6 | 8 | 14 | Mitigate | Develop and deliver comprehensive training programs for all users. Provide ongoing support and resources to address user queries and issues. | New | 4w/$35,000 | $10,000 | Mitigate | Tailor training materials to user roles and skill levels | Establish a help desk or support team for immediate assistance | TBD
Note on B1: List the Risk Number in sequential order, 1, 2 etc.
Note on C1: List the deliverables associated with the risk. Tie back to the requirements number, test case number, request for change number or WBS number. If a deliverable cannot be tied, leave this blank
Note on D1: Describe the risk - an event or condition, which if it occurs, has a positive or negative affect on a project's objectives, (i.e.: The technology that is being purchased will not be supported by the manufacturer in 2 months).
Note on E1: Risk Categories are sources of potential risk for classification. List the appropriate risk categories: (Refer to the Risk Identification Category Checklist for memory joggers). Chose from the list.
Note on F1: State how the risk would affect the project if it occurs, (i.e.: not having manufacturer support for this technology would be have an adverse affect to the roll out).
Note on G1: List the name of the person that has ownership of this risk, and the ownership to make certain the response plan is implemented.
Note on H1: Indicate the likelihood that the risk will occur using the scale - Low, Medium, or High. Low - one in every 3 years, Medium - once every year, High - once during the project.
Note on I1: State how the risk could affect the project if it occurs using the scale - Low, Medium, or High. Low - less than 10% of the project budget, Medium - 10 -25% of the project budget, High - more than 25% of the project budget.
Note on L1: The overall risk assessment is the sum of the likelihood of occurrence and the impact. The risk assessment will be automatically calculated when using the spreadsheet. The minimum threshold for completing a Risk Response Form is 5. If this number is 5 or greater, complete the Risk Response Form.
Note on M1: Choose from the one of the responses below. Acceptance: Accept the consequences - do nothing, no changes to the project direction. Avoidance: Eliminate the cause of the risk - change the project direction to protect the project objectives from this impact. Mitigation: Take action to reduce the probability that the risk will occur to an acceptable threshold. Transference: Transfer the responsibility of managing the risk, including ownership, and acceptance of consequences. Transference does not eliminate the risk.
Note on N1: Provide details describing the selected response.
Note on O1: Choose from the drop down box.
Note on U1: List the date the response strategy was implemented mm/dd/yy.