## Assignment 6
WBS# | Task Name | Duration | Start | Finish | Dependencies | Assigned To | Work Effort | Cost | Status | Indicator
1 | Initialize & Conceptualize | 55d | 2024-07-01 | 2024-08-24 |  |  |  |  | Not Started | Red
1.1 | Identify project scope | 15d | 2024-07-01 | 2024-07-15 |  | Jake Towers; Kris Watson; Kevin Simon; DCS |  |  | Not Started | Red
1.1.1 | Conduct stakeholder interviews to gather initial requirements and document stakeholder interview notes. | 5d | 2024-07-01 | 2024-07-05 |  | Delta Consultancy Services |  |  | Not Started | Red
1.1.1.1 | Prepare interview questions | 2d | 2024-07-01 | 2024-07-02 |  | Anubhav | 8 man-hours | 200 | Not Started | Red
1.1.1.2 | Schedule interviews with stakeholders | 1d | 2024-07-03 | 2024-07-03 | 4 | Silky | 12 man-hours | 200 | Not Started | Red
1.1.1.3 | Conduct stakeholder interviews | 1d | 2024-07-04 | 2024-07-04 | 5 | Atish | 20 man-hours | 400 | Not Started | Red
1.1.1.4 | Document stakeholder interview notes | 1d | 2024-07-05 | 2024-07-05 | 6 | Atish, Harika | 16 man-hours | 200 | Not Started | Red
1.1.2 | Define project boundaries and deliverables, and produce the project scope statement document. | 10d | 2024-07-06 | 2024-07-15 |  | Delta Consultancy Services |  |  | Not Started | Red
1.1.2.1 | Review stakeholder interview notes | 2d | 2024-07-06 | 2024-07-07 | 7 | Harika | 8 man-hours | 600 | Not Started | Red
1.1.2.2 | Identify project boundaries | 2d | 2024-07-08 | 2024-07-09 | 9 | Silky | 10 man-hours | 200 | Not Started | Red
1.1.2.3 | Produce project scope statement document | 6d | 2024-07-10 | 2024-07-15 | 10 | Anubhav | 16 man-hours | 900 | Not Started | Red
1.2 | Develop a preliminary business case | 21d | 2024-07-06 | 2024-07-26 |  | Kevin Simon; DCS |  |  | Not Started | Red
1.2.1 | Conduct market research and feasibility analysis, resulting in the creation of a market research report and feasibility study document. | 4d | 2024-07-06 | 2024-07-09 |  | Delta Consultancy Services |  |  | Not Started | Red
1.2.1.1 | Conduct market research | 1d | 2024-07-06 | 2024-07-06 | 7 | Harika | 80 man-hours | 3000 | Not Started | Red
1.2.1.2 | Perform feasibility analysis | 1d | 2024-07-07 | 2024-07-07 | 14 | Anubhav | 40 man-hours | 1500 | Not Started | Red
1.2.1.3 | Create market research report | 1d | 2024-07-07 | 2024-07-07 | 14 | Atish | 24 man-hours | 900 | Not Started | Red
1.2.1.4 | Generate feasibility study document | 2d | 2024-07-08 | 2024-07-09 | 15, 16 | Anubhav | 32 man-hours | 1200 | Not Started | Red
1.2.2 | Identify potential risks and mitigation strategies, updating the risk register and risk management plan. | 11d | 2024-07-16 | 2024-07-26 |  |  |  |  | Not Started | Red
1.2.2.1 | Identify potential risks | 5d | 2024-07-16 | 2024-07-20 | 11, 17 | Silky | 32 man-hours | 900 | Not Started | Red
1.2.2.2 | Update risk register and management plan | 6d | 2024-07-21 | 2024-07-26 | 19 | Atish | 16 man-hours | 900 | Not Started | Red
1.3 | Obtain approval to proceed | 29d | 2024-07-27 | 2024-08-24 |  | Jake Towers; DCS |  |  | Not Started | Red
1.3.1 | Present the preliminary business case to stakeholders for approval, and generate the business case presentation and approval document. | 15d | 2024-07-27 | 2024-08-10 |  | Delta Consultancy Services |  |  | Not Started | Red
1.3.1.1 | Prepare preliminary business case presentation | 4d | 2024-07-27 | 2024-07-30 | 15, 20 | Anubhav and Silky | 24 man-hours | 900 | Not Started | Red
1.3.1.2 | Present the preliminary business case to stakeholders for approval | 4d | 2024-07-31 | 2024-08-03 | 23 | Harika | 8 man-hours | 300 | Not Started | Red
1.3.1.3 | Generate the business case presentation and approval document | 7d | 2024-08-04 | 2024-08-10 | 24 | Harika | 16 man-hours | 600 | Not Started | Red
1.3.2 | Secure funding and resources for the project, creating budget allocation and resource plan documents. | 14d | 2024-08-11 | 2024-08-24 |  | Delta Consultancy Services |  |  | Not Started | Red
1.3.2.1 | Identify funding sources and resource requirements | 2d | 2024-08-11 | 2024-08-12 | 25 | Harika | 16 man-hours | 600 | Not Started
1.3.2.2 | Develop budget allocation plan | 3d | 2024-08-13 | 2024-08-15 | 27 | Anubhav | 24 man-hours | 900 | Not Started
1.3.2.3 | Create resource plan document | 4d | 2024-08-16 | 2024-08-19 | 28 | Silky | 16 man-hours | 600 | Not Started
1.3.2.4 | Secure funding from identified sources | 5d | 2024-08-20 | 2024-08-24 | 29 | Atish | 40 man-hours | 1500 | Not Started
2 | Project Charter & Plan | 26d | 2024-07-27 | 2024-08-21 |  |  |  |  | Not Started | Red
2.1 | Draft the project charter | 17d | 2024-07-27 | 2024-08-12 |  | Jake Towers, Kris Watson, Kevin Simon; DCS |  |  | Not Started | Red
2.1.1 | Define project objectives, scope, and success criteria, and produce the project charter document. | 10d | 2024-07-27 | 2024-08-05 |  | Delta Consultancy Services |  |  | Not Started | Red
2.1.1.1 | Define project objectives | 2d | 2024-07-27 | 2024-07-28 | 20 | Project Manager, Stakeholders | 16 man-hours | 600 | Not Started | Red
2.1.1.2 | Define project scope | 3d | 2024-07-29 | 2024-07-31 | 34 | Project Manager, Stakeholders | 24 man-hours | 900 | Not Started | Red
2.1.1.3 | Define success criteria | 2d | 2024-08-01 | 2024-08-02 | 35 | Project Manager, Stakeholders | 16 man-hours | 600 | Not Started | Red
2.1.1.4 | Produce the project charter document | 3d | 2024-08-03 | 2024-08-05 | 36 | Project Manager | 24 man-hours | 900 | Not Started | Red
2.1.2 | Identify project team members and their roles, updating the organizational chart and roles and responsibilities matrix. | 7d | 2024-08-06 | 2024-08-12 |  | Delta Consultancy Services |  |  | Not Started | Red
2.1.2.1 | Identify project team members and their roles | 3d | 2024-08-06 | 2024-08-08 | 37 | Silky, Harika, Atish, Bhumika, Anubhav | 48 man-hours | 1800 | Not Started | Red
2.1.2.2 | Update the organizational chart | 2d | 2024-08-09 | 2024-08-10 | 39 | Harika, Atish, Bhumika, Anubhav | 32 man-hours | 1200 | Not Started | Red
2.1.2.3 | Update roles and responsibilities matrix | 2d | 2024-08-11 | 2024-08-12 | 40 | Atish, Bhumika, Anubhav, Silky | 32 man-hours | 1200 | Not Started | Red
2.2 | Define project objectives and constraints | 5d | 2024-08-06 | 2024-08-10 |  | Kevin Simon; DCS |  |  | Not Started | Red
2.2.1 | Conduct a SWOT analysis to identify strengths, weaknesses, opportunities, and threats, resulting in a SWOT analysis report. | 3d | 2024-08-06 | 2024-08-08 |  | Delta Consultancy Services |  |  | Not Started | Red
2.2.1.2 | Conduct SWOT analysis | 2d | 2024-08-06 | 2024-08-07 | 37 | Harika, Bhumika, Atish, Anubhav | 64 man-hours | 2400 | Not Started | Red
2.2.1.3 | Produce SWOT analysis report | 1d | 2024-08-08 | 2024-08-08 | 44 | Harika, Bhumika, Atish, Anubhav | 32 man-hours | 1200 | Not Started | Red
2.2.2 | Define project constraints such as budget, timeline, and resources, updating the project constraints document. | 5d | 2024-08-06 | 2024-08-10 |  | Delta Consultancy Services |  |  | Not Started | Red
2.2.2.1 | Define project constraints | 2d | 2024-08-06 | 2024-08-07 | 37 | Silky, Atish, Bhumika, Anubhav | 32 man-hours | 1200 | Not Started | Red
2.2.2.2 | Update project constraints document | 2d | 2024-08-09 | 2024-08-10 | 45, 47 | Silky, Atish, Bhumika, Anubhav | 16 man-hours | 600 | Not Started | Red
2.3 | Develop a detailed project plan | 11d | 2024-08-11 | 2024-08-21 |  | Jake Towers, Kris Watson, Kevin Simon; DCS |  |  | Not Started | Red
2.3.1 | Create a work breakdown structure (WBS) with tasks, dependencies, and milestones, and generate the WBS and project schedule. | 5d | 2024-08-11 | 2024-08-15 |  | Delta Consultancy Services |  |  | Not Started | Red
2.3.1.1 | Create Work Breakdown Structure (WBS) | 3d | 2024-08-11 | 2024-08-13 | 48 | Harika, Bhumika, Atish, Anubhav | 48 man-hours | 1800 | Not Started | Red
2.3.1.2 | Generate project schedule | 2d | 2024-08-14 | 2024-08-15 | 51, 48 | Harika, Bhumika, Atish, Anubhav | 32 man-hours | 1200 | Not Started | Red
2.3.2 | Develop a project schedule, resource allocation plan, and risk management plan, updating the resource plan and risk management plan documents. | 6d | 2024-08-16 | 2024-08-21 |  | Delta Consultancy Services |  |  | Not Started | Red
2.3.2.1 | Develop project schedule | 1d | 2024-08-16 | 2024-08-16 | 52 | Harika, Bhumika, Atish, Anubhav | 48 man-hours | 1800 | Not Started | Red
2.3.2.2 | Create resource allocation plan | 2d | 2024-08-17 | 2024-08-18 | 54 | Harika, Bhumika, Atish, Anubhav | 32 man-hours | 1200 | Not Started | Red
2.3.2.3 | Develop risk management plan | 3d | 2024-08-17 | 2024-08-19 | 54 | Harika, Bhumika, Atish, Anubhav | 64 man-hours | 2400 | Not Started | Red
2.3.2.4 | Update resource plan document | 2d | 2024-08-19 | 2024-08-20 | 55 | Harika, Bhumika, Atish, Anubhav | 32 man-hours | 1200 | Not Started | Red
2.3.2.5 | Update risk management plan document | 2d | 2024-08-20 | 2024-08-21 | 56 | Harika, Bhumika, Atish, Anubhav | 32 man-hours | 1200 | Not Started | Red
3 | Execute & Control | 105d | 2024-08-11 | 2024-11-23 |  |  |  |  | Not Started | Red
3.1 | Requirement Gathering & Analysis | 25d | 2024-08-11 | 2024-09-04 |  | Kevin Simon; DCS |  |  | Not Started | Red
3.1.1 | Conduct stakeholder workshops to gather detailed requirements and document the requirements gathering workshop report and requirements traceability matrix. | 9d | 2024-08-11 | 2024-08-19 |  | Delta Consultancy Services |  |  | Not Started | Red
3.1.1.1 | Conduct stakeholder workshops | 2d | 2024-08-11 | 2024-08-12 | 25 | Silky, Harika, Atish, Anubhav | 80 man-hours | 3000 | Not Started | Red
3.1.1.2 | Document requirements gathering workshop report | 3d | 2024-08-13 | 2024-08-15 | 62 | Silky, Harika, Atish, Anubhav | 48 man-hours | 1800 | Not Started | Red
3.1.1.3 | Develop requirements traceability matrix | 4d | 2024-08-16 | 2024-08-19 | 63 | Silky, Harika, Atish, Anubhav | 64 man-hours | 2400 | Not Started | Red
3.1.2 | Analyze requirements using techniques like use cases, user stories, and mockups, producing use case documents, user stories, and mockups. | 11d | 2024-08-20 | 2024-08-30 |  | Delta Consultancy Services |  |  | Not Started | Red
3.1.2.1 | Analyze requirements using techniques | 2d | 2024-08-20 | 2024-08-21 | 64 | Bhumika, Atish, Anubhav, Silky | 64 man-hours | 2400 | Not Started | Red
3.1.2.2 | Produce use case documents | 2d | 2024-08-22 | 2024-08-23 | 66 | Bhumika, Atish, Anubhav, Silky | 48 man-hours | 1800 | Not Started | Red
3.1.2.3 | Develop user stories | 3d | 2024-08-24 | 2024-08-26 | 67 | Bhumika, Atish, Anubhav, Silky | 48 man-hours | 1800 | Not Started | Red
3.1.2.4 | Create mockups | 4d | 2024-08-27 | 2024-08-30 | 68 | Bhumika, Atish, Anubhav, Silky | 64 man-hours | 2400 | Not Started | Red
3.1.3 | Prioritize requirements based on business value and impact, updating the requirements prioritization matrix. | 5d | 2024-08-31 | 2024-09-04 |  | Delta Consultancy Services |  |  | Not Started | Red
3.1.3.1 | Prioritize requirements based on business value and impact | 2d | 2024-08-31 | 2024-09-01 | 69 | Harika, Bhumika, Atish, Anubhav | 48 man-hours | 1800 | Not Started | Red
3.1.3.2 | Update requirements prioritization matrix | 3d | 2024-09-02 | 2024-09-04 | 71 | Harika, Bhumika, Atish, Anubhav | 32 man-hours | 1200 | Not Started | Red
3.2 | Design & Architecture | 14d | 2024-09-05 | 2024-09-18 |  | Kevin Simon; DCS |  |  | Not Started | Red
3.2.1 | Develop a high-level system architecture and data flow diagram, resulting in the creation of system architecture and data flow diagrams. | 4d | 2024-09-05 | 2024-09-08 |  | Delta Consultancy Services |  |  | Not Started | Red
3.2.1.1 | Develop high-level system architecture | 2d | 2024-09-05 | 2024-09-06 | 72 | Anubhav, Silky, Harika, Atish | 64 man-hours | 2400 | Not Started | Red
3.2.1.2 | Create data flow diagram | 2d | 2024-09-07 | 2024-09-08 | 75 | Anubhav, Silky, Harika, Atish | 48 man-hours | 1800 | Not Started | Red
3.2.2 | Create detailed technical design documents for each module and update technical design specifications. | 2d | 2024-09-09 | 2024-09-10 |  | Delta Consultancy Services |  |  | Not Started | Red
3.2.2.1 | Create detailed technical design documents for each module | 1d | 2024-09-09 | 2024-09-09 | 76 | Atish, Bhumika, Silky, Harika | 64 man-hours | 2400 | Not Started | Red
3.2.2.2 | Update technical design specifications | 1d | 2024-09-10 | 2024-09-10 | 78 | Atish, Bhumika, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
3.2.3 | Review design documents with stakeholders and obtain approvals, updating design review meeting minutes and design approval documents. | 8d | 2024-09-11 | 2024-09-18 |  | Delta Consultancy Services |  |  | Not Started | Red
3.2.3.1 | Review design documents with stakeholders | 1d | 2024-09-11 | 2024-09-11 | 78, 79 | Harika, Bhumika, Atish, Anubhav | 48 man-hours | 1800 | Not Started | Red
3.2.3.2 | Obtain approvals | 2d | 2024-09-12 | 2024-09-13 | 81 | Harika, Bhumika, Atish, Anubhav | 32 man-hours | 1200 | Not Started | Red
3.2.3.3 | Update design review meeting minutes | 2d | 2024-09-14 | 2024-09-15 | 82 | Harika, Bhumika, Atish, Anubhav | 16 man-hours | 600 | Not Started | Red
3.2.3.4 | Update design approval documents | 3d | 2024-09-16 | 2024-09-18 | 83 | Harika, Bhumika, Atish, Anubhav | 16 man-hours | 600 | Not Started | Red
3.3 | Module Development | 22d | 2024-09-19 | 2024-10-10 |  | Kevin Simon; DCS |  |  | Not Started | Red
3.3.1 | Develop code for each module based on technical design specifications, producing source code files and a coding standards document. | 6d | 2024-09-19 | 2024-09-24 |  | Delta Consultancy Services |  |  | Not Started | Red
3.3.1.1 | Develop code for each module based on technical design specifications | 2d | 2024-09-19 | 2024-09-20 | 84 | Atish, Bhumika, Silky, Harika | 80 man-hours | 3000 | Not Started | Red
3.3.1.2 | Produce source code files | 2d | 2024-09-21 | 2024-09-22 | 87 | Atish, Bhumika, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
3.3.1.3 | Create coding standards document | 2d | 2024-09-23 | 2024-09-24 | 88 | Atish, Bhumika, Silky, Harika | 16 man-hours | 600 | Not Started | Red
3.3.2 | Conduct code reviews and unit testing for quality assurance, updating code review reports and unit test results. | 11d | 2024-09-25 | 2024-10-05 |  | Delta Consultancy Services |  |  | Not Started | Red
3.3.2.1 | Conduct code reviews for quality assurance | 2d | 2024-09-25 | 2024-09-26 | 89 | Anubhav, Silky, Harika, Atish | 64 man-hours | 2400 | Not Started | Red
3.3.2.2 | Perform unit testing | 2d | 2024-09-27 | 2024-09-28 | 91 | Anubhav, Silky, Harika, Atish | 48 man-hours | 1800 | Not Started | Red
3.3.2.3 | Update code review reports | 3d | 2024-09-29 | 2024-10-01 | 92 | Anubhav, Silky, Harika, Atish | 16 man-hours | 600 | Not Started | Red
3.3.2.4 | Update unit test results | 4d | 2024-10-02 | 2024-10-05 | 93 | Anubhav, Silky, Harika, Atish | 16 man-hours | 600 | Not Started | Red
3.3.3 | Integrate modules and perform integration testing, generating integration test plans and integration test results. | 5d | 2024-10-06 | 2024-10-10 |  | Delta Consultancy Services |  |  | Not Started | Red
3.3.3.1 | Integrate modules and perform integration testing | 1d | 2024-10-06 | 2024-10-06 | 94 | Anubhav, Silky, Harika, Atish | 80 man-hours | 3000
3.3.3.2 | Generate integration test plans | 1d | 2024-10-07 | 2024-10-07 | 96 | Anubhav, Silky, Harika, Atish | 48 man-hours | 1800
3.3.3.3 | Produce integration test results | 3d | 2024-10-08 | 2024-10-10 | 97 | Anubhav, Silky, Harika, Atish | 48 man-hours | 1800
3.4 | Testing | 25d | 2024-10-11 | 2024-11-04 |  | Kevin Simon; DCS |  |  | Not Started | Red
3.4.1 | Develop detailed test plans covering functional, performance, and security testing, producing test plans, test cases, and test data. | 9d | 2024-10-11 | 2024-10-19 |  | Delta Consultancy Services |  |  | Not Started | Red
3.4.1.1 | Develop detailed test plans covering functional, performance, and security testing | 2d | 2024-10-11 | 2024-10-12 | 98 | Bhumika, Atish, Silky, Harika | 80 man-hours | 3000 | Not Started | Red
3.4.1.2 | Create test cases | 3d | 2024-10-13 | 2024-10-15 | 101 | Bhumika, Atish, Silky, Harika | 48 man-hours | 1800 | Not Started | Red
3.4.1.3 | Prepare test data | 4d | 2024-10-16 | 2024-10-19 | 102 | Bhumika, Atish, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
3.4.2 | Execute test cases and document test results, updating test execution reports and defect reports. | 11d | 2024-10-20 | 2024-10-30 |  | Delta Consultancy Services |  |  | Not Started | Red
3.4.2.1 | Execute test cases | 2d | 2024-10-20 | 2024-10-21 | 103 | Silky, Atish, Bhumika, Harika | 64 man-hours | 2400 | Not Started | Red
3.4.2.2 | Document test results | 3d | 2024-10-22 | 2024-10-24 | 105 | Silky, Atish, Bhumika, Harika | 48 man-hours | 1800 | Not Started | Red
3.4.2.3 | Update test execution reports | 2d | 2024-10-25 | 2024-10-26 | 106 | Silky, Atish, Bhumika, Harika | 16 man-hours | 600 | Not Started | Red
3.4.2.4 | Update defect reports | 4d | 2024-10-27 | 2024-10-30 | 107 | Silky, Atish, Bhumika, Harika | 16 man-hours | 600 | Not Started | Red
3.4.3 | Perform regression testing and bug tracking, updating regression test results and the bug tracking log. | 5d | 2024-10-31 | 2024-11-04 |  | Delta Consultancy Services |  |  | Not Started | Red
3.4.3.1 | Perform regression testing | 2d | 2024-10-31 | 2024-11-01 | 108 | Silky, Atish, Bhumika, Harika | 64 man-hours | 2400
3.4.3.2 | Track bugs | 1d | 2024-11-02 | 2024-11-02 | 110 | Silky, Atish, Bhumika, Harika | 48 man-hours | 1800
3.4.3.3 | Update regression test results | 1d | 2024-11-03 | 2024-11-03 | 111 | Silky, Atish, Bhumika, Harika | 32 man-hours | 1200
3.4.3.4 | Update bug tracking log | 1d | 2024-11-04 | 2024-11-04 | 112 | Silky, Atish, Bhumika, Harika | 32 man-hours | 1200
3.5 | Implementation | 66d | 2024-09-19 | 2024-11-23 |  | Jake Towers, Kris Watson, Kevin Simon; DCS |  |  | Not Started | Red
3.5.1 | Prepare user documentation, training materials, and system manuals, producing user manuals, training guides, and system documentation. | 9d | 2024-11-05 | 2024-11-13 |  | Delta Consultancy Services |  |  | Not Started | Red
3.5.1.1 | Prepare user documentation | 2d | 2024-11-05 | 2024-11-06 | 113 | Harika, Bhumika, Atish, Silky | 64 man-hours | 2400 | Not Started | Red
3.5.1.2 | Develop training materials | 3d | 2024-11-07 | 2024-11-09 | 116 | Harika, Bhumika, Atish, Silky | 48 man-hours | 1800 | Not Started | Red
3.5.1.3 | Produce system manuals | 4d | 2024-11-10 | 2024-11-13 | 117 | Harika, Bhumika, Atish, Silky | 32 man-hours | 1200 | Not Started | Red
3.5.2 | Conduct user training sessions and system demos, updating training attendance records and feedback surveys. | 10d | 2024-11-14 | 2024-11-23 |  | Delta Consultancy Services |  |  | Not Started | Red
3.5.2.1 | Conduct user training sessions | 1d | 2024-11-14 | 2024-11-14 | 118 | Atish, Bhumika, Silky, Harika | 64 man-hours | 2400 | Not Started | Red
3.5.2.2 | Perform system demos | 2d | 2024-11-15 | 2024-11-16 | 120 | Atish, Bhumika, Silky, Harika | 48 man-hours | 1800 | Not Started | Red
3.5.2.3 | Update training attendance records | 3d | 2024-11-17 | 2024-11-19 | 121 | Atish, Bhumika, Silky, Harika | 16 man-hours | 600 | Not Started | Red
3.5.2.4 | Collect feedback through surveys | 4d | 2024-11-20 | 2024-11-23 | 122 | Atish, Bhumika, Silky, Harika | 16 man-hours | 600 | Not Started | Red
3.5.3 | Deploy the SMS Application System in the live environment and monitor for any issues, generating a deployment plan, deployment checklist, and post-implementation review report. | 57d | 2024-09-19 | 2024-11-14 |  | Delta Consultancy Services |  |  | Not Started | Red
3.5.3.1 | Generate deployment plan | 1d | 2024-09-19 | 2024-09-19 | 84 | Anubhav, Silky, Harika, Atish | 48 man-hours | 1800 | Not Started | Red
3.5.3.2 | Create deployment checklist | 2d | 2024-09-20 | 2024-09-21 | 125 | Anubhav, Silky, Harika, Atish | 32 man-hours | 1200 | Not Started | Red
3.5.3.3 | Deploy the SMS Application System in the live environment | 3d | 2024-11-05 | 2024-11-07 | 113 | Anubhav, Silky, Harika, Atish | 64 man-hours | 2400 | Not Started | Red
3.5.3.4 | Monitor for any issues | 4d | 2024-11-08 | 2024-11-11 | 127 | Anubhav, Silky, Harika, Atish | 32 man-hours | 1200 | Not Started | Red
3.5.3.5 | Generate post-implementation review report | 3d | 2024-11-12 | 2024-11-14 | 128 | Anubhav, Silky, Harika, Atish | 32 man-hours | 1200 | Not Started | Red
4 | Close Project | 17d | 2024-11-15 | 2024-12-01 |  |  |  |  | Not Started | Red
4.1 | Prepare final project report | 9d | 2024-11-15 | 2024-11-23 |  | Jake Towers, Kris Watson, Kevin Simon, DCS |  |  | Not Started | Red
4.1.1 | Summarize project objectives, achievements, and lessons learned, and produce the final project report and lessons learned document. | 9d | 2024-11-15 | 2024-11-23 |  | Delta Consultancy Services |  |  | Not Started | Red
4.1.1.1 | Summarize project objectives, achievements, and lessons learned | 2d | 2024-11-15 | 2024-11-16 | 129 | Bhumika, Atish, Silky, Harika | 64 man-hours | 2400 | Not Started | Red
4.1.1.2 | Produce the final project report | 3d | 2024-11-17 | 2024-11-19 | 133 | Bhumika, Atish, Silky, Harika | 48 man-hours | 1800 | Not Started | Red
4.1.1.3 | Create the lessons learned document | 4d | 2024-11-20 | 2024-11-23 | 134 | Bhumika, Atish, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
4.1.2 | Document project outcomes, deliverables, and final budget allocation, updating the project outcomes report and budget allocation report. | 7d | 2024-11-15 | 2024-11-21 |  | Delta Consultancy Services |  |  | Not Started | Red
4.1.2.1 | Document project outcomes, deliverables, and final budget allocation | 2d | 2024-11-15 | 2024-11-16 | 129 | Silky, Atish, Harika, Bhumika | 64 man-hours | 2400 | Not Started | Red
4.1.2.2 | Update the project outcomes report | 3d | 2024-11-17 | 2024-11-19 | 137 | Silky, Atish, Harika, Bhumika | 32 man-hours | 1200 | Not Started | Red
4.1.2.3 | Update the budget allocation report | 2d | 2024-11-20 | 2024-11-21 | 138 | Silky, Atish, Harika, Bhumika | 32 man-hours | 1200 | Not Started | Red
4.2 | Obtain formal acceptance of deliverables | 14d | 2024-11-15 | 2024-11-28 |  | Jake Towers, DCS |  |  | Not Started | Red
4.2.1 | Review deliverables with stakeholders and obtain sign-off, updating the deliverable acceptance document and sign-off sheet. | 8d | 2024-11-15 | 2024-11-22 |  | Delta Consultancy Services |  |  | Not Started | Red
4.2.1.1 | Review deliverables with stakeholders | 1d | 2024-11-15 | 2024-11-15 | 129 | Harika, Bhumika, Atish, Silky | 48 man-hours | 1800 | Not Started | Red
4.2.1.2 | Obtain sign-off | 2d | 2024-11-16 | 2024-11-17 | 142, 127 | Harika, Bhumika, Atish, Silky | 32 man-hours | 1200 | Not Started | Red
4.2.1.3 | Update deliverable acceptance document | 2d | 2024-11-18 | 2024-11-19 | 143 | Harika, Bhumika, Atish, Silky | 16 man-hours | 600 | Not Started | Red
4.2.1.4 | Update sign-off sheet | 3d | 2024-11-20 | 2024-11-22 | 144 | Harika, Bhumika, Atish, Silky | 16 man-hours | 600 | Not Started | Red
4.2.2 | Address any outstanding issues or feedback from stakeholders, updating the issue resolution log and stakeholder feedback report. | 6d | 2024-11-23 | 2024-11-28 |  | Delta Consultancy Services |  |  | Not Started | Red
4.2.2.1 | Address outstanding issues or feedback from stakeholders | 1d | 2024-11-23 | 2024-11-23 | 145 | Atish, Bhumika, Silky, Harika | 64 man-hours | 2400 | Not Started | Red
4.2.2.2 | Update issue resolution log | 2d | 2024-11-24 | 2024-11-25 | 147 | Atish, Bhumika, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
4.2.2.3 | Update stakeholder feedback report | 3d | 2024-11-26 | 2024-11-28 | 148 | Atish, Bhumika, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
4.3 | Close out all aspects of the project | 3d | 2024-11-29 | 2024-12-01 |  | Kevin Simon, DCS |  |  | Not Started | Red
4.3.1 | Archive project documents, code repositories, and test results, updating the project archive, code repository backup, and test results archive. | 3d | 2024-11-29 | 2024-12-01 |  | Delta Consultancy Services |  |  | Not Started | Red
4.3.1.1 | Archive project documents | 2d | 2024-11-29 | 2024-11-30 | 149 | Bhumika, Atish, Silky, Harika | 48 man-hours | 1800 | Not Started | Red
4.3.1.2 | Backup code repositories | 3d | 2024-11-29 | 2024-12-01 | 149 | Bhumika, Atish, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
4.3.1.3 | Store test results | 2d | 2024-11-29 | 2024-11-30 | 149 | Bhumika, Atish, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
4.3.1.4 | Update project archive | 3d | 2024-11-29 | 2024-12-01 | 149 | Bhumika, Atish, Silky, Harika | 16 man-hours | 600 | Not Started | Red
4.3.1.5 | Backup code repository | 2d | 2024-11-29 | 2024-11-30 | 149 | Bhumika, Atish, Silky, Harika | 16 man-hours | 600 | Not Started | Red
4.3.1.6 | Update test results archive | 3d | 2024-11-29 | 2024-12-01 | 149 | Bhumika, Atish, Silky, Harika | 16 man-hours | 600 | Not Started | Red
5 | Evaluate Project Success | 35d | 2024-12-02 | 2025-01-05 |  |  |  |  | Not Started | Red
5.1 | Conduct post-project evaluations with stakeholders | 14d | 2024-12-02 | 2024-12-15 |  | Jake Towers, Kris Watson, Kevin Simon, DCS |  |  | Not Started | Red
5.1.1 | Gather feedback on project performance, user satisfaction, and business impact, updating the post-project evaluation survey and stakeholder feedback analysis report. | 7d | 2024-12-02 | 2024-12-08 |  | Delta Consultancy Services |  |  | Not Started | Red
5.1.1.1 | Gather feedback on project performance, user satisfaction, and business impact | 2d | 2024-12-02 | 2024-12-03 | 135, 139, 145, 157 | Silky, Atish, Bhumika, Harika | 64 man-hours | 2400 | Not Started | Red
5.1.1.2 | Update post-project evaluation survey | 3d | 2024-12-04 | 2024-12-06 | 161 | Silky, Atish, Bhumika, Harika | 32 man-hours | 1200 | Not Started | Red
5.1.1.3 | Update stakeholder feedback analysis report | 2d | 2024-12-07 | 2024-12-08 | 162 | Silky, Atish, Bhumika, Harika | 32 man-hours | 1200 | Not Started | Red
5.1.2 | Identify areas of improvement and future opportunities, updating improvement recommendations and opportunity identification report. | 7d | 2024-12-09 | 2024-12-15 |  | Delta Consultancy Services |  |  | Not Started | Red
5.1.2.1 | Identify areas of improvement and future opportunities | 2d | 2024-12-09 | 2024-12-10 | 163 | Harika, Bhumika, Atish, Silky | 64 man-hours | 2400 | Not Started | Red
5.1.2.2 | Update improvement recommendations | 2d | 2024-12-11 | 2024-12-12 | 165 | Harika, Bhumika, Atish, Silky | 32 man-hours | 1200 | Not Started | Red
5.1.2.3 | Update opportunity identification report | 3d | 2024-12-13 | 2024-12-15 | 166 | Harika, Bhumika, Atish, Silky | 32 man-hours | 1200 | Not Started | Red
5.2 | Document lessons learned | 14d | 2024-12-16 | 2024-12-29 |  | Jake Towers, Kris Watson, Kevin Simon, DCS |  |  | Not Started | Red
5.2.1 | Document key insights, best practices, and lessons learned during the project, updating the lessons learned document and best practices guide. | 7d | 2024-12-16 | 2024-12-22 |  | Delta Consultancy Services |  |  | Not Started | Red
5.2.1.1 | Document key insights, best practices, and lessons learned | 2d | 2024-12-16 | 2024-12-17 | 167 | Atish, Bhumika, Silky, Harika | 64 man-hours | 2400 | Not Started | Red
5.2.1.2 | Update lessons learned document | 3d | 2024-12-18 | 2024-12-20 | 170 | Atish, Bhumika, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
5.2.1.3 | Update best practices guide | 2d | 2024-12-21 | 2024-12-22 | 171 | Atish, Bhumika, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
5.2.2 | Share lessons learned with the project team and stakeholders for continuous improvement, updating the lessons learned presentation and knowledge sharing sessions. | 7d | 2024-12-23 | 2024-12-29 |  | Delta Consultancy Services |  |  | Not Started | Red
5.2.2.1 | Share lessons learned with the project team and stakeholders | 2d | 2024-12-23 | 2024-12-24 | 172 | Bhumika, Atish, Silky, Harika | 64 man-hours | 2400 | Not Started | Red
5.2.2.2 | Update lessons learned presentation | 2d | 2024-12-25 | 2024-12-26 | 174 | Bhumika, Atish, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
5.2.2.3 | Conduct knowledge sharing sessions | 3d | 2024-12-27 | 2024-12-29 | 175 | Bhumika, Atish, Silky, Harika | 32 man-hours | 1200 | Not Started | Red
5.3 | Archive all project documents | 7d | 2024-12-30 | 2025-01-05 |  | Jake Towers, Kris Watson, Kevin Simon, DCS |  |  | Not Started | Red
5.3.1 | Store project documents, reports, and artifacts in a centralized repository for future reference and audit purposes, updating the project documentation repository and audit trail. | 7d | 2024-12-30 | 2025-01-05 |  | Delta Consultancy Services |  |  | Not Started | Red
5.3.1.1 | Store project documents, reports, and artifacts | 2d | 2024-12-30 | 2024-12-31 | 176 | Silky, Atish, Bhumika, Harika | 64 man-hours | 2400 | Not Started | Red
5.3.1.2 | Update project documentation repository | 3d | 2025-01-01 | 2025-01-03 | 179 | Silky, Atish, Bhumika, Harika | 32 man-hours | 1200 | Not Started | Red
5.3.1.3 | Update audit trail | 2d | 2025-01-04 | 2025-01-05 | 180 | Silky, Atish, Bhumika, Harika | 32 man-hours | 1200 | Not Started | Red